## Slide 1: SCRUM MASTER AND PRODUCT OWNER BOOTCAMP
RSM+RPO

## Slide 2: BACKLOG PRIORITIZATION
SCRUM BOOTCAMP

## Slide 3
Value
Compliance Risk
Enabling
Customer /Market
Effort
Estimation Tools
Affinity
Planning Poker
Techniques
WSJF
Cost of Delay

## Slide 4: Business Value Vision Updated on a Regular Cadence
Jan
Each Sprint
Monthly
Quarterly
Yearly
User story planning
Backlog refinement
Sprint goals
Actual financial performance
Epic progress check-in
Epic definition/prioritization
Release planning
Financial Forecasts and goals
Incremental Funding
Strategic goals
Financial estimates
Multiple parallel planning, review, and retrospective cadences

## Slide 5: Cost of Delay Example
Project B2B Commerce has cost of delay of $10M per month
Time
Cost of Delay
Feature | Cost of Delay ($M/month) | Duration (months)
Project | 10 | 8
Project
Total Cost of Delay = $80M
Time
Total Cost of Delay = $50M
Feature | Cost of Delay ($M/month) | Duration (months)
A - Lookup | 4 | 1
B – Buy | 1 | 5
C - Status | 5 | 2
B
$6
$40
C
$4
A
Total Cost of Delay = $27M
A
$4
C
$15
B
$8
Feature | Cost of Delay ($M/month) | Duration (months) | CD3
A - Lookup | 4 | 1 | 4.0
B – Buy | 1 | 5 | 0.2
C - Status | 5 | 2 | 2.5

## Slide 6: SLICING USER STORIES
SCRUM BOOTCAMP

## Slide 7
https://www.mountaingoatsoftware.com/uploads/documents/spidr-poster.pdf